## Slide 1
IMPLEMENTATION PROPOSAL
Bosley HairClub
UKG Pro Merger
August 2026
BOSLEY
HairClub
PREPARED FOR BOSLEY HAIRCLUB
© 2026 AlignHCM · Confidential
Align HCM · 01

## Slide 2
BOSLEY HAIRCLUB · UKG PRO MERGER
Executive Summary
Bosley HairClub is bringing approximately 400 employees onto HairClub's existing UKG Pro environment, migrating them off ADP.
400 employees, ADP to UKG Pro
Bosley HairClub's ~400 employees move from ADP onto HairClub's existing UKG Pro environment.
Existing business rules apply
Bosley employees will be set up under HairClub's existing business rules, pay rules, and accrual rules already in production.
Scope: Pro, WFM, data & onboarding
Project management, UKG Pro / WFM system configuration, and data conversion.
16-week timeline
12 weeks of implementation plus 4 weeks of post go-live support, targeting a January 1, 2027 go-live (actual go-live is the first pay in January and first punch on the first day of that pay period).
alignhcm.com
© 2026 AlignHCM · Confidential
Align HCM · 02

## Slide 3
16 WEEKS TO GO-LIVE
Proposed Timeline
16 weeks total: 12-week implementation + 4 weeks of post go-live support.
Kickoff &
Planning
Wk 1-2
Analysis &
Validation
Wk 2-5
Configuration
& Build
Wk 4-8
Data
Conversion
Wk 7-10
Testing &
UAT
Wk 9-11
Post Go-Live
Support
Wk 13-16
GO-LIVE
Week 12
Weeks 1-12 · Implementation
Weeks 13-16 · Post Go-Live
Target go-live: January 1, 2027, with true go-live defined as the start of the first supported pay period.
alignhcm.com
© 2026 AlignHCM · Confidential
Align HCM · 03

## Slide 4
PHASE BY PHASE
Milestones by Phase
What gets delivered, and when, across the 16-week engagement.
Phase | Weeks | Key Milestones
Kickoff & Planning | Wk 1-2 | Project kickoff, team alignment, environment access, project plan finalized
Analysis & Validation | Wk 2-5 | Validate Bosley population against HairClub's existing business, pay, and accrual rules; confirm component company structure
Configuration & Build | Wk 4-8 | Component company setup in UKG Pro, WFM configuration walkthroughs, integration updates
Data Conversion | Wk 7-10 | Convert and load Bosley employee data from ADP; validate demographic, pay, and accrual data
Testing & UAT | Wk 9-11 | Parallel payroll testing, user acceptance testing, sign-off
Go-Live | Wk 12 | Bosley employees live on UKG Pro; first supported payroll processed
Post Go-Live Support | Wk 13-16 | Hypercare support, issue resolution, transition to steady state
alignhcm.com
© 2026 AlignHCM · Confidential
Align HCM · 04

## Slide 5
PHASE 1 INVESTMENT
AlignHCM — Planned Investment
Total project cost for a January 1, 2027 go-live.
$93,955
Total project investment · 1/1/2027 go-live
Includes project management, UKG Pro & WFM system configuration, and employee data conversion.
+$12,900 for an earlier go-live
If Bosley HairClub goes live sooner than 1/1/2027, an additional $12,900 applies for the extra data conversion work required to bring over opening balances.
12 weeks of implementation + 4 weeks of post go-live support = 16 weeks total
Pricing reflects Phase 1 only: bringing Bosley HairClub's 400 employees onto HairClub's existing UKG Pro environment. Phase 2 (Benefits Hub) will be scoped and priced separately.
alignhcm.com
© 2026 AlignHCM · Confidential
Align HCM · 05

## Slide 6
YOUR TEAM'S ROLE
What We'll Need From Your Team
Estimated level of engagement by project phase.
Resource | Kickoff | Analysis | Build & Convert | Test | Go-Live
Project Lead | Medium | Medium | Medium | Medium | Low
HR / Payroll SME | Low | High | Medium | High | Medium
System Administrator | Low | Medium | High | Medium | Medium
IT / Data Contact | Low | Low | High | Low | Low
Your team stays focused on decisions and validation
HairClub's team confirms that Bosley employees fit existing business rules, validates converted data, and supports UAT sign-off. AlignHCM leads configuration, data conversion, and testing coordination.
alignhcm.com
© 2026 AlignHCM · Confidential
Align HCM · 06

## Slide 7
NEXT STEP
Let's stay connected!
Allison Cox
Client Executive
allison.cox@alignhcm.com
317-690-7960
alignhcm.com
© 2026 AlignHCM · Confidential · 07