## Executive Summary
AUTHORITY HUB // DELIVERY REVIEW
Proposal alignment, reconstructed effort, and release evidence · August 21, 2026
THE READOUT
TOTAL RECONSTRUCTED |  | ORIGINAL PROPOSAL |  | ADDED VALUE |  | REVIEW STATE
35 |  | 31.5 |  | 3.5 |  | 2 LIVE DIRECTIONS
hours |  | hours |  | hours |  | both noindex
EFFORT BY WORKSTREAM
Workstream | Hours
Discovery & Audit | 4
Search Strategy | 4.5
Content System | 11
Technical & WordPress | 6.5
Roadmaps & Workflow | 3.75
Review & Handoff | 1.75
Added-Value Experiences | 3.5
WHAT THIS SHEET IS |  |  |  |  | HONEST PRODUCTION BOUNDARY
A transparent reconstruction of effort from dated artifacts, proposal workstreams, and delivery evidence. It is not minute-by-minute timekeeping. The 35.00-hour total combines 31.50 hours mapped to the original proposal and 3.50 hours of added-value hardcoded experience work. |  |  |  |  | The proposal artifacts and two review experiences are ready for client review. The WordPress pillar is still gated by Janice's factual approval, final CMS settings, staging QA, and explicit publication approval. The Netlify concepts remain noindex review builds.
Source window: August 3–21, 2026 · Reconstructed August 21, 2026 · BigOrange Marketing Authority Hub

## Effort Log
RECONSTRUCTED EFFORT LOG
35.00 hours mapped to dated work products and proposal commitments
Method: reconstructed from file evidence and work categories; not presented as precise stopwatch records.
Date | Workstream | Activity | Scope Class | Hours | Status | Proposal Commitment | Evidence / Artifact
2026-08-03 12:00 | Discovery & Audit | Audit the live builder page, content structure, mobile experience, and technical baseline. | Original Proposal | 2 | Complete | Current-site audit | live-site-technical-audit-2026-08-20.md
2026-08-03 12:00 | Discovery & Audit | Review builder-agency competitors, page patterns, positioning gaps, and proof conventions. | Original Proposal | 2 | Complete | Competitor research | competitor-research.md
2026-08-04 12:00 | Search Strategy | Reconcile Emilia's historical Moz export with current Semrush evidence and filter the usable commercial-intent set. | Original Proposal | 3 | Complete | Keyword research and rationale | keyword-strategy-2026-08-20.md
2026-08-04 12:00 | Content System | Map the authority hub, buyer questions, supporting pages, proof sequence, and conversion path. | Original Proposal | 1.5 | Complete | Content architecture | content-architecture.md
2026-08-05 12:00 | Content System | Complete internal-link routes and the protect, improve, build, reject search-intent architecture. | Original Proposal | 1.5 | Complete | Content architecture | keyword-strategy-2026-08-20.md
2026-08-05 12:00 | Search Strategy | Build the AEO/GEO answer, entity, evidence, and citation-readiness strategy. | Original Proposal | 1.5 | Complete | AI-search strategy | ai-search-strategy.md
2026-08-06 12:00 | Content System | Write and structure the first half of the custom home builder pillar production candidate. | Original Proposal | 2 | Production candidate | One complete pillar | wordpress/pillar-page.md
2026-08-07 12:00 | Content System | Finish the pillar copy, proof blocks, calls to action, and WordPress-ready structure. | Original Proposal | 2 | Production candidate | One complete pillar | wordpress/pillar-page.html
2026-08-08 12:00 | Content System | Write supporting article one around builder website must-haves and lead quality. | Original Proposal | 1.25 | Production candidate | Two supporting articles | wordpress/supporting-article-01.md
2026-08-08 12:00 | Content System | Write supporting article two around essential home builder blog topics. | Original Proposal | 1.25 | Production candidate | Two supporting articles | wordpress/supporting-article-02.md
2026-08-09 12:00 | Content System | Create the visible FAQ set and matching answer-ready schema copy. | Original Proposal | 1.5 | Production candidate | FAQ set | wordpress/pillar-page.html
2026-08-10 12:00 | Technical & WordPress | Specify title, description, canonical, social metadata, and production URL handling. | Original Proposal | 0.75 | Complete spec | Metadata and canonicals | wordpress/seo-metadata.json
2026-08-10 12:00 | Technical & WordPress | Build the Organization, WebSite, WebPage, Service, Breadcrumb, and FAQ schema graph. | Original Proposal | 0.75 | Complete spec | Schema | wordpress/schema-graph.json
2026-08-10 12:00 | Technical & WordPress | Document breadcrumbs, sitemap, and internal-link implementation requirements. | Original Proposal | 1 | Complete spec | Breadcrumbs, XML sitemap, and internal links | wordpress/qa-checklist.md
2026-08-11 12:00 | Technical & WordPress | Create the mobile, payload, image, JavaScript, and Core Web Vitals work order. | Original Proposal | 1 | Complete work order | Core Web Vitals and mobile plan | wordpress/qa-checklist.md
2026-08-12 12:00 | Technical & WordPress | Assemble the editable Beaver Builder and native-editor production candidate modules. | Original Proposal | 2 | Private review build | WordPress implementation | wordpress/beaver-builder-assembly-guide.md
2026-08-12 12:00 | Technical & WordPress | QA the reversible WordPress package, metadata, content order, and staging checklist. | Original Proposal | 1 | Private review build | WordPress implementation | wordpress/qa-checklist.md
2026-08-13 12:00 | Roadmaps & Workflow | Build the 90-day implementation roadmap with dependencies and acceptance gates. | Original Proposal | 1 | Complete | 90-day roadmap | 90-day-roadmap.md
2026-08-13 12:00 | Roadmaps & Workflow | Extend the operating plan into a 12-month opportunity and measurement roadmap. | Original Proposal | 0.5 | Complete | 12-month bonus roadmap | 12-month-roadmap.md
2026-08-14 12:00 | Roadmaps & Workflow | Document the human-approved AI editorial workflow and two-hour production target. | Original Proposal | 0.75 | Complete | AI-assisted editorial workflow | ai-assisted-editorial-workflow.md
2026-08-14 12:00 | Roadmaps & Workflow | Build Janice's SME interview guide and factual-approval handoff. | Original Proposal | 0.75 | Complete guide | SME interview workflow | janice-sme-interview-guide.md
2026-08-14 12:00 | Roadmaps & Workflow | Create the builder marketing readiness checklist and downloadable PDF. | Original Proposal | 0.75 | Complete | Downloadable asset | downloads/BigOrange-Builder-Marketing-Readiness-Checklist.pdf
2026-08-20 12:00 | Review & Handoff | Reconcile the proposal line by line, package evidence, and build the final review story. | Original Proposal | 1.75 | Updated candidate | Final presentation | delivery-completion-matrix-2026-08-20.md
2026-08-21 12:00 | Added-Value Experiences | Design, code, humanize, optimize, deploy, and QA the Industry Signal hardcoded experience. | Added Value | 1.75 | Live review build | Industry Signal experience | https://bigorange-marketing-homepage.netlify.app/
2026-08-21 12:00 | Added-Value Experiences | Design, code, humanize, optimize, deploy, and QA the Primary Portfolio hardcoded experience. | Added Value | 1.75 | Live review build | Primary Portfolio experience | https://bigorange-marketing-homepage.netlify.app/primary/
TOTAL RECONSTRUCTED HOURS |  |  |  | 35 | 31.50 proposal + 3.50 added-value hours

## Proposal Alignment
PROPOSAL ALIGNMENT // WHAT EXISTS, WHAT REMAINS
Every artifact that can truthfully exist before Janice's interview is present. Publication remains gated.
Commitment | State | Deliverable / Evidence | Reconstructed Hours | Remaining Gate | Scope
Current-site audit | Complete | live-site-technical-audit-2026-08-20.md | 2 | No remaining research gate | Original proposal
Competitor research | Complete | competitor-research.md | 2 | No remaining research gate | Original proposal
Keyword research and rationale | Complete | keyword-strategy-2026-08-20.md | 3 | Preserve the current ranking moat while improving weaker exact-fit terms | Original proposal
Content architecture | Complete | content architecture plus internal-link plan | 3 | Apply inside the approved WordPress build | Original proposal
AI-search strategy | Complete | AEO/GEO answer and entity strategy | 1.5 | Validate citations and AI-referral measurement after launch | Original proposal
90-day roadmap | Complete | 90-day-roadmap.md | 1 | Begin after Janice and staging gates | Original proposal
12-month bonus roadmap | Complete | 12-month-roadmap.md | 0.5 | Sequence against real capacity and results | Original proposal bonus
One complete pillar | Production candidate | wordpress/pillar-page.md and .html | 4 | Janice factual review, final CMS metadata, and publication approval | Original proposal
Two supporting articles | Production candidate | wordpress/supporting-article-01/02 | 2.5 | Janice review, category, featured image, and staging QA | Original proposal
FAQ set | Production candidate | visible answers plus matching FAQ schema | 1.5 | Janice review and final visible/schema parity check | Original proposal
Metadata and canonicals | Complete spec | wordpress/seo-metadata.json | 0.75 | Apply and verify in staging | Original proposal
Schema | Complete spec | wordpress/schema-graph.json | 0.75 | Validate in staging and prevent plugin duplication | Original proposal
Breadcrumbs, XML sitemap, and internal links | Complete spec | wordpress/qa-checklist.md | 1 | Apply and verify in staging and production | Original proposal
Core Web Vitals and mobile plan | Complete work order | wordpress/qa-checklist.md | 1 | Theme and plugin implementation plus confirmation run | Original proposal
WordPress implementation | Private review build | Beaver Builder and native-editor packages | 3 | Choose assembly path, stage, QA, and approve | Original proposal
AI-assisted editorial workflow | Complete | ai-assisted-editorial-workflow.md | 0.75 | Measure the first real editorial cycle | Original proposal
SME interview workflow | Complete guide | janice-sme-interview-guide.md | 0.75 | Conduct Janice interview and record approvals | Original proposal
Downloadable asset | Complete | Builder Marketing Readiness Checklist PDF | 0.75 | Approve placement and form path | Original proposal
Final presentation | Updated candidate | new executive delivery PDF plus completion matrix | 1.75 | Insert Janice-approved examples and staging results | Original proposal
Editorial target at or below two hours | Designed; measurement pending | AI-assisted editorial workflow | 0 | Measure the first approved production cycle | Original proposal
Final acceptance and publication | Gated | delivery-completion-matrix-2026-08-20.md | 0 | Janice approval, CMS settings, staging QA, and explicit publication approval | Original proposal
Industry Signal experience | Live review build | Netlify review URL | 1.75 | Select if this becomes the production direction | Added value
Primary Portfolio experience | Live review build | Netlify /primary/ review URL | 1.75 | Select if this becomes the production direction | Added value

## Evidence Index
EVIDENCE INDEX // REVIEWABLE SOURCE OF TRUTH
Paths are relative to the canonical BigOrange deliverable unless a live URL is shown.
Artifact | Type | Proposal Link | Current State | Path / URL | Verified Date
Live-site technical audit | Audit | Current-site audit | Complete | live-site-technical-audit-2026-08-20.md | 2026-08-20 12:00
Competitor research | Research | Competitor research | Complete | competitor-research.md | 2026-08-20 12:00
Keyword strategy | Research | Keyword research and rationale | Complete | keyword-strategy-2026-08-20.md | 2026-08-20 12:00
Pillar production candidate | Content | One complete pillar | Production candidate | wordpress/pillar-page.html | 2026-08-21 12:00
Supporting article one | Content | Two supporting articles | Production candidate | wordpress/supporting-article-01.html | 2026-08-20 12:00
Supporting article two | Content | Two supporting articles | Production candidate | wordpress/supporting-article-02.html | 2026-08-20 12:00
SEO metadata | Technical | Metadata and canonicals | Complete spec | wordpress/seo-metadata.json | 2026-08-20 12:00
Schema graph | Technical | Schema | Complete spec | wordpress/schema-graph.json | 2026-08-20 12:00
Beaver Builder assembly guide | WordPress | WordPress implementation | Private review build | wordpress/beaver-builder-assembly-guide.md | 2026-08-20 12:00
90-day roadmap | Roadmap | 90-day roadmap | Complete | 90-day-roadmap.md | 2026-08-20 12:00
12-month roadmap | Roadmap | 12-month bonus roadmap | Complete | 12-month-roadmap.md | 2026-08-20 12:00
AI editorial workflow | Workflow | AI-assisted editorial workflow | Complete | ai-assisted-editorial-workflow.md | 2026-08-20 12:00
Janice SME interview guide | Workflow | SME interview workflow | Complete guide | janice-sme-interview-guide.md | 2026-08-20 12:00
Builder Marketing Readiness Checklist | Download | Downloadable asset | Complete | downloads/BigOrange-Builder-Marketing-Readiness-Checklist.pdf | 2026-08-20 12:00
Delivery completion matrix | Handoff | Final presentation | Complete | delivery-completion-matrix-2026-08-20.md | 2026-08-20 12:00
Industry Signal | Live review experience | Industry Signal experience | Live, noindex | https://bigorange-marketing-homepage.netlify.app/ | 2026-08-21 12:00
Primary Portfolio | Live review experience | Primary Portfolio experience | Live, noindex | https://bigorange-marketing-homepage.netlify.app/primary/ | 2026-08-21 12:00
Netlify deployment | Deployment receipt | Two live review experiences | Production deploy complete | deploy 6a88c72d33044244bcca1e01 | 2026-08-21 12:00