BIGORANGE.MARKETING

Custom Home Builder
Authority System

Final Pilot Proposal and Leadership Decision Packet

Interview-integrated content, keyword ownership, release plan, measurement, and next-phase roadmap

| 62 KEYWORD DECISIONS | 19 OWNED ASSETS | 3 PILOT DRAFTS | 90 DAY RELEASE PLAN |
| --- | --- | --- | --- |

DECISION PURPOSE  Approve the exact authority-hub direction and review gates, then release one coherent builder-marketing system without fragmenting the existing commercial URL.

| Proposal field | Confirmed position |
| --- | --- |
| Prepared for | Margee, Paula, Janice, and BigOrange leadership |
| Prepared by | Dillon Mohr, DM Marketing Specialist |
| Prepared | August 28, 2026 |
| Pilot truth | 35 hours at $30/hour; approved total $1,050 |
| Decision date | September 3, 2026 leadership review |
| Status | Complete proposal package; publication remains approval gated |

CONFIDENTIAL WORKING PROPOSAL  |  NO PUBLIC CLAIM OR PUBLICATION IS IMPLIED

BIGORANGE AUTHORITY SYSTEM

# Executive decision

What leadership is approving and why it is ready now.

RECOMMENDATION  Approve one authority hub at the existing /marketing-agency-for-builders/ URL, select a single visual direction, and release the pillar plus two supporting articles only after Janice closes factual and public-use permissions.

## The system being approved

This pilot converts a broad builder-services page into a focused authority system for custom home builders while preserving the existing URL that already owns relevant commercial intent. The system is deliberately smaller than the full keyword universe: one hub, distinct supporting reader jobs, explicit internal links, governed evidence, and a review loop that learns from real queries and qualified actions.

The final package now includes the audit and research foundation, the 62-query decision ledger, a 19-asset ownership map, the revised pillar, two complete supporting articles, a visible FAQ and schema candidate, a 90-day release sequence, a 12-month roadmap, AI-search implementation guidance, and publication QA gates.

## Why this is stronger after Janice's interview

The audience is framed around real builder growth moments: uneven pipeline, referrals slowing, an aging website, stretched internal marketing capacity, succession, or a shift into a new service mix.

Trust is treated as a proof sequence, not a slogan: excellent project photography, current digital presence, customer evidence, a clear process, direct answers, and a low-pressure next step.

The content answers questions builders commonly leave unresolved, including pricing guidance, site work, permits, architecture, land, design-build responsibility, and what marketing support actually includes.

The plan separates demand generation from sales follow-up. A raised hand is not automatically a qualified opportunity, and the lead definition remains a leadership decision instead of a fabricated metric.

EVIDENCE BOUNDARY  Janice sent the recordings for analysis, but the formal public-use permission readback was not captured. Only the anonymized Homearama example has explicit paraphrase permission. Every other interview-derived public claim remains a factual-review draft.

BIGORANGE AUTHORITY SYSTEM

# Commercial truth and scope

A final proposal should make the approved commitment unmistakable and keep future work separate.

| 35 APPROVED HOURS | $30 HOURLY RATE | $1,050 APPROVED TOTAL |
| --- | --- | --- |

## Included in the current pilot

Audit of the current builder page and surrounding authority opportunity.

Competitor and keyword research, content architecture, and AI-search strategy.

One interview-integrated authority hub and two complete supporting articles.

Implementation specification, metadata, internal-link logic, FAQ/schema candidate, and release QA gates.

90-day roadmap, governed editorial workflow, final leadership packet, and bonus 12-month roadmap.

## Mapped, but not produced in this pilot

Ongoing social post production.

A broader downloadable asset beyond the mapped checklist and worksheet concepts.

Video production or a webinar.

The eleven next-phase articles, guides, subpillars, galleries, and tools in the authority roadmap.

PRICING BOUNDARY  This packet does not invent a next-phase price. Cadence, production mix, ownership, revision allowance, payment timing, and acceptance mechanics must be scoped after leadership chooses the continuation model.

| State | Commercial position |
| --- | --- |
| Confirmed | 35 hours, $30/hour, $1,050 total, pilot deliverables, Phase 2 exclusions |
| Decision required | Invoice recipient and timing, payment timing, revision allowance, acceptance, ownership, confidentiality, portfolio use |
| Not claimed | Payment receipt, publication, traffic growth, ranking gains, lead volume, revenue, AI citations, or rich results |

BIGORANGE AUTHORITY SYSTEM

# The content authority system

One commercial owner, distinct supporting jobs, and a complete path from discovery to qualified conversation.

## The hub-and-spoke model

- Attract. Capture builder-specific informational and commercial questions through distinct pages that match a real reader job.

- Prove. Use original expertise, project photography, process evidence, client-approved examples, and direct answers that reduce uncertainty.

- Connect. Link every supporting asset to the canonical builder hub and to the next logical decision page without creating duplicate intent.

- Convert. Offer a low-pressure next step and preserve enough context for sales to evaluate fit, response time, and follow-up status.

- Learn. Review actual queries, engagement, assisted actions, and lead-quality feedback before expanding the cluster.

## Three production-ready pilot assets

| ID | Draft | Approx. length | Primary next step |
| --- | --- | --- | --- |
| HUB-01 | Custom Home Builder Marketing That Builds Trust Before the First Call | 2,564 words | Schedule a non-sales call |
| ART-01 | Why Your Home Builder Website Is Not Generating Qualified Leads | 1,292 words | Request a builder website clarity review |
| ART-02 | 5 Articles Every Custom Home Builder Blog Needs | 1,060 words | Schedule a builder content planning call |

## Canonical ownership rules

HUB-01 owns agency, company, firm, services, solutions, system, and broad home-builder-marketing commercial variations.

ART-01 owns the diagnostic intent around a website not generating leads and website optimization; WEB-01 owns design, development, and service-comparison intent.

ART-02 owns home builder blog and editorial-ideas intent; CNT-01 owns the broader content-marketing operating system.

VIS-01 owns broad SEO and digital-visibility intent; LOCAL-01 owns local SEO; SEOCHK-01 owns the narrow on-page phrase/checklist intent.

STR-01 owns marketing plans, strategies, and tips; AUD-01 owns market segments and new-builder audience framing.

No asset is published until its reader job, primary query, canonical, and reciprocal internal links are documented.

BIGORANGE AUTHORITY SYSTEM

# Pilot content: what is ready

The copy is complete as a review draft; claims and publication remain gated.

HUB-01  |  EXISTING AUTHORITY HUB

## Custom Home Builder Marketing That Builds Trust Before the First Call

Primary query owner: custom home builder marketing. Primary CTA: Schedule a non-sales call.

Leads with excellent work and project photography instead of generic agency claims.

Frames the marketing problem around trust, clarity, proof, discoverability, demand, and follow-up.

Addresses referrals, an aging website, uneven pipeline, DIY marketing, and the 'work should speak for itself' objection.

Preserves /marketing-agency-for-builders/ as the single commercial owner.

ART-01  |  SUPPORTING DIAGNOSTIC ARTICLE

## Why Your Home Builder Website Is Not Generating Qualified Leads

Primary query owner: home builder website not generating leads. Primary CTA: Request a builder website clarity review.

Separates low traffic, poor-fit traffic, weak proof, unclear scope, friction, and incomplete follow-up.

Gives a corrective sequence instead of treating a redesign as the automatic answer.

Supports the hub without competing for agency or service-page intent.

Creates a natural bridge to the website-design subpillar and SEO checklist.

ART-02  |  SUPPORTING EDITORIAL ARTICLE

## 5 Articles Every Custom Home Builder Blog Needs

Primary query owner: home builder blog. Primary CTA: Schedule a builder content planning call.

Turns repeated buyer questions into five durable article types tied to actual decisions.

Explains how one SME interview can support articles, FAQs, email, sales follow-up, social, and video planning.

Keeps the broader content-marketing system for CNT-01 to prevent duplication.

Ends with a planning conversation rather than a ranking promise.

COMPANION COPY PACKAGE  The complete editable pillar, two complete articles, visible FAQ set, and matching FAQ schema candidate are included beside this proposal for line-by-line review and WordPress implementation.

BIGORANGE AUTHORITY SYSTEM

# Keyword and intent strategy

The 62-row ledger is a decision system, not a promise to publish 62 pages.

| 62 QUERIES REVIEWED | 58 ASSIGNED | 4 REJECTED | 1 CANONICAL HUB |
| --- | --- | --- | --- |

The keyword plan combines dated Semrush demand and difficulty evidence, dated Moz rank and URL evidence, live-site verification, funnel intent, reader job, and ownership. Blank evidence is treated as unknown, not as zero. The workbook preserves all raw fields and separates build decisions from source limitations.

## Priority clusters

| Cluster | Owner | Representative demand |
| --- | --- | --- |
| Core authority | HUB-01 | custom home builder marketing; home builder marketing; agency/company/firm variations |
| Visibility | VIS-01 / LOCAL-01 | SEO for home builders; SEO for custom home builders; local SEO for home builders |
| Website | ART-01 / WEB-01 / GAL-01 | website not generating leads; website design; examples; best websites |
| Strategy and audience | STR-01 / AUD-01 | marketing plan; strategies; target market segments; new home builder marketing |
| Lead operations | LEAD-01 / NUR-01 / AUTO-01 | lead generation; CRM; email; nurture; automation; sales alignment |
| Content | ART-02 / CNT-01 / SOC-01 | home builder blog; content marketing; social media marketing |

## Rejected and validate-first demand

Reject generic agency terms such as 'digital marketing agency' and 'SEO agency' for this focused pilot.

Reject homeowner-intent queries such as 'custom home builders near me' and 'how much does a custom home cost.'

Validate ambiguous phrases such as 'custom home builder website,' website classification criteria, and home builder market research before production.

Protect the existing hub's commercial relevance rather than splitting near-synonyms into thin competing pages.

BIGORANGE AUTHORITY SYSTEM

# The 19-asset portfolio

Every keyword has an owner, every owner has a reader job, and every build window is explicit.

SCOPE READ  Three assets are complete current-pilot drafts. Eleven assets are mapped as next-phase production candidates. Social production is explicitly Phase 2, while the remaining assets stay in backlog or validate-first state.

| ID | Asset | Window | State |
| --- | --- | --- | --- |
| HUB-01 | Custom Home Builder Marketing That Builds Trust Before the First Call | Current pilot | Complete interview-integrated draft |
| ART-01 | Why Your Home Builder Website Is Not Generating Qualified Leads | Current pilot | Complete interview-integrated draft |
| ART-02 | 5 Articles Every Custom Home Builder Blog Needs | Current pilot | Complete interview-integrated draft |
| STR-01 | A Practical Home Builder Marketing Plan | Days 31-60 / next phase | Brief ready; production not included in current pilot |
| VIS-01 | SEO, Local Search, and AI Visibility for Home Builders | Days 31-60 / next phase | Brief ready; production not included in current pilot |
| WEB-01 | Home Builder Website Design, Proof, and Conversion | Days 31-60 / next phase | Brief ready; production not included in current pilot |
| AUD-01 | Custom Home Builder Target Market Segments | Days 31-60 / next phase | Brief ready; production not included in current pilot |
| LEAD-01 | Home Builder Lead Generation and Follow-Up | Days 61-90 / next phase | Brief ready; production not included in current pilot |
| LOCAL-01 | Local SEO for Home Builders: Markets, Reviews, and Proof | Days 31-60 / next phase | Brief ready; production not included in current pilot |
| NUR-01 | Home Builder Email Marketing, CRM, and Lead Nurture | Days 61-90 / next phase | Brief ready; production not included in current pilot |
| AUTO-01 | Marketing Automation for Home Builders Without Losing the Human Touch | Days 61-90 / next phase | Brief ready; production not included in current pilot |
| SOC-01 | Social Media Marketing for Home Builders | Phase 2 | Brief ready; production explicitly excluded from current pilot |
| CNT-01 | Home Builder Content Marketing That Answers Real Buyer Questions | Days 31-60 / next phase | Brief ready; production not included in current pilot |
| GAL-01 | Best Home Builder Websites: Examples and Evaluation Criteria | Days 61-90 / next phase | Brief ready; production not included in current pilot |
| TPL-01 | Home Builder Website Templates and Platforms: What to Evaluate | Backlog / after authority foundation | Brief ready; production not included in current pilot |
| SEOCHK-01 | Recommended Phrases and Page Elements for Home Builder Website SEO | Days 31-60 / next phase | Brief ready; production not included in current pilot |
| MKTRES-01 | Home Builder Market Research: A Practical Framework | Quarter 2 or 3 after proof assets | Validate intent and methodology before production |
| PPC-01 | PPC for Home Builders | Backlog | Deferred until conversion tracking and proof are validated |
| CONSULT-01 | Home Builder Marketing Consulting | Backlog | Do not build until leadership confirms a distinct offer and non-cannibalizing intent |

BIGORANGE AUTHORITY SYSTEM

# 90-day release and expansion plan

The first 30 days are a governed release sequence. Expansion begins only after the foundation is verified.

| Timing | Asset / gate | Scope | Current state |
| --- | --- | --- | --- |
| Gate 0 | Approval and source closure | Current pilot | Blocked on reviewers |
| Week 1 | HUB-01, ART-01, ART-02 | Current pilot | Drafts ready for review |
| Week 2 | Technical release package | Current pilot | Specification ready |
| Week 3 | WordPress staging | Current pilot | Requires staging target |
| Week 4 | Foundation release | Current pilot | Approval gated |
| Week 5 | Release verification | Current pilot | After publication |
| Week 6 | STR-01 | Next phase | Not included in current pilot |
| Week 7 | VIS-01 | Next phase | Not included in current pilot |
| Week 8 | WEB-01 | Next phase | Not included in current pilot |
| Week 9 | LOCAL-01 | Next phase | Not included in current pilot |
| Week 10 | AUD-01 | Next phase | Not included in current pilot |
| Week 11 | LEAD-01 | Next phase | Not included in current pilot |
| Week 12 | Quarterly authority review | Next phase | No outcome forecast |

## Release logic

- Gate 0. Close Janice factual and permission review, leadership direction, imagery, owners, and the staging target.

- Weeks 1-2. Close copy, metadata, links, technical requirements, analytics, CRM, schema, accessibility, performance, and rollback preparation.

- Weeks 3-5. Assemble staging, run final QA, publish only the exact approved revision, then verify the live result separately.

- Weeks 6-12. Build the first next-phase subpillars only under a separately approved production scope and refreshed evidence.

EXPECTATION SETTING  Ninety days is enough to launch a healthy foundation and learn from early demand signals. Six months is the more realistic window for momentum. This is a sequencing principle, not a traffic, lead, or revenue forecast.

BIGORANGE AUTHORITY SYSTEM

# 12-month authority roadmap

A sustainable rhythm: one substantial asset, one meaningful refresh, one proof or tool, and one measurement question.

| Month | Focus | Primary asset | Measurement question |
| --- | --- | --- | --- |
| 1 | Approve and release the foundation | HUB-01, ART-01, ART-02 | Indexation, tracking, lead-definition baseline |
| 2 | Strategy and audience | STR-01 | Query mix and consultation path |
| 3 | Visibility | VIS-01 and LOCAL-01 | Search Console, local/entity consistency |
| 4 | Website conversion | WEB-01 | CTA path and qualified actions |
| 5 | Audience fit | AUD-01 | Market/project fit feedback |
| 6 | Lead handoff | LEAD-01 and NUR-01 | Response time, acceptance, nurture status |
| 7 | Content engine | CNT-01 | Editorial time, content use, assisted actions |
| 8 | Automation | AUTO-01 | Follow-up completion and exceptions |
| 9 | Visual proof | GAL-01 | Project-page engagement and next steps |
| 10 | Short-form distribution | SOC-01 if separately approved | Qualified assisted visits, not vanity reach |
| 11 | Platform decisions | TPL-01 and SEOCHK-01 | Decision support and sales use |
| 12 | Research and consolidation | MKTRES-01 only with a defensible method | Qualified demand and assisted pipeline after validation |

The roadmap is a planning model, not a production commitment. Each month requires an owner, approved scope, current source review, claim permissions, and release QA. Underperforming or overlapping assets should be refreshed, consolidated, or pruned rather than multiplied.

BIGORANGE AUTHORITY SYSTEM

# SEO, AI-search, and technical implementation

Useful original content, clear ownership, and crawlable structure are the strategy; there is no separate AI-search shortcut.

## Implementation principles

- Preserve one representative URL. Keep the existing builder URL as the canonical commercial hub. Supporting assets own distinct reader jobs and link back to it.

- Make expertise attributable. Use named reviewers, first-hand observations, original visuals, dated sources, and explicit claim permissions.

- Answer the whole decision. Provide direct answers, scope clarity, process, proof, objections, and a logical next step instead of producing shallow query variants.

- Keep machine-readable markup honest. Use schema only when it matches visible content and the page type. Do not duplicate organization, breadcrumb, or FAQ markup.

- Measure field performance. Use Search Console and real-user Core Web Vitals data for actual evaluation. Lab tools guide diagnosis but are not proof of field experience.

- Control crawlers intentionally. Review search and training crawler policy as a business decision. Do not change robots.txt reflexively or imply that access guarantees inclusion.

## Page-level release specification

Confirm title, meta description, one H1, canonical, breadcrumbs, indexability, and sitemap behavior.

Install reciprocal internal links and document the reader job and primary query owner.

Match visible FAQ copy and FAQ schema exactly; do not promise a Google FAQ rich result.

Verify desktop/mobile layout, keyboard and focus behavior, reduced motion, overflow, accessibility, forms, console output, analytics, and performance.

Record a rollback snapshot and owner before publication, then verify the live rendered state after release.

NO GUARANTEE  No ranking, traffic, lead, revenue, AI citation, answer-engine inclusion, featured snippet, or rich-result outcome is promised in this proposal.

BIGORANGE AUTHORITY SYSTEM

# Measurement and lead handoff

The scorecard separates visibility, engagement, qualified actions, sales handling, and business outcomes.

| Layer | What to observe | Source | Cadence |
| --- | --- | --- | --- |
| Technical foundation | Indexation, canonical selected by Google, sitemap status, crawl errors, Core Web Vitals | Search Console, field data, release log | After release and monthly |
| Demand visibility | Query mix, impressions, clicks, landing pages, nonbrand visibility | Search Console and dated rank tools | Monthly; no guaranteed target |
| Content usefulness | Engaged sessions, scroll depth where configured, CTA progression, internal-link paths | Analytics and behavior instrumentation | Monthly |
| Qualified actions | Consultation requests, calls, form completions, downloads, assisted actions | Analytics and CRM reconciliation | Weekly / monthly |
| Sales handling | Response time, acceptance, owner, status, nurture completion, disqualification reason | CRM and sales-owner review | Weekly |
| Business outcome | Qualified opportunities and assisted pipeline only after definitions and attribution are validated | CRM and financial evidence | Quarterly |

## Qualified-lead definition to complete

Audience and market fit: builder type, geography, service area, and project type.

Business fit: need, urgency, decision authority, current capacity, and willingness to invest.

Engagement fit: raised-hand action, requested service, context supplied, and response status.

Sales outcome: accepted, nurture, disqualified with reason, or no response after documented follow-up.

OPEN DEFINITION  Janice described an MQL as a raised hand, but the full scoring model was not completed in the recorded interview. Leadership and sales must approve the definition before any conversion claim is used.

BIGORANGE AUTHORITY SYSTEM

# Editorial governance and permissions

Interview insight becomes public content only through a documented review path.

## Claim lifecycle

- Capture. Record the source, speaker, date, timestamp, working claim, and intended asset.

- Classify. Mark the claim as experience, opinion, process, terminology, estimate, or client example.

- Verify. Check every number, name, result, award, ranking, timeframe, and platform behavior against an original source.

- Permission. Assign an explicit public-use code and required anonymization. Silence is not permission.

- Edit. Convert approved evidence into precise reader-facing language without adding magnitude or certainty.

- Release. Publish only the exact reviewed revision, then verify the live page separately.

## Interview material currently held

Audience boundaries across custom builders, production builders, developers, master-planned communities, and remodelers.

Any revenue or business-maturity threshold.

Trigger moments, trust factors, photography guidance, website questions, referral limits, objections, and terminology.

The full qualified-lead definition and measurement language.

EXPLICIT PERMISSION  The anonymized Homearama example may be paraphrased. The visitor estimate, named client, timeframe, performance implication, and any other result still require independent verification before use.

BIGORANGE AUTHORITY SYSTEM

# September 3 leadership decisions

The system is ready for a bounded approval conversation, not an open-ended rewrite.

| # | Decision | Required resolution |
| --- | --- | --- |
| 1 | Visual direction | Choose Cinematic Authority, Orange Press, or an explicitly bounded hybrid. |
| 2 | Canonical owner | Confirm /marketing-agency-for-builders/ remains the one authority hub. |
| 3 | Approvers | Name owners for copy, claims, visuals, technical changes, publication, and rollback. |
| 4 | Staging | Confirm the WordPress staging target, production target, access path, and rollback owner. |
| 5 | Imagery | Approve hero, project photography, article featured images, releases, and alt-text owner. |
| 6 | Measurement | Approve the scorecard and complete the qualified-lead definition. |
| 7 | Continuation | Choose next-phase cadence, deliverable mix, ownership, and production scope. |
| 8 | Commercial terms | Confirm invoice/payment timing, revisions, acceptance, ownership, confidentiality, and portfolio use. |

## Janice review checklist

Confirm audience boundaries and remove or confirm the tentative maturity threshold.

Approve the edited positioning, trust, photography, website, referral, pricing-guidance, and objection language.

Approve five to eight visible FAQ answers and matching schema candidate.

Complete the qualified-lead definition.

Approve or reject the anonymized Homearama paraphrase and assign public-use codes to all other interview language.

BIGORANGE AUTHORITY SYSTEM

# Acceptance and release gates

Completion of the proposal is not the same as approval, publication, or verified live performance.

## Pilot package acceptance

Leadership confirms the packet reflects the approved 35-hour pilot and no additional production has been implied.

Janice confirms factual accuracy and permission states for interview-derived language.

Leadership selects the visual direction and exact WordPress revision path.

Commercial mechanics are documented: invoice, payment, revisions, acceptance, ownership, confidentiality, and portfolio use.

The content workbook and companion drafts are accepted as the operating source package for implementation.

## Publication gate

Approved copy and imagery are installed in staging.

Metadata, canonical, breadcrumbs, internal links, sitemap behavior, and schema are verified without duplication.

Visible FAQ copy and FAQ schema match exactly.

Desktop/mobile, keyboard/focus, reduced motion, overflow, accessibility, console, links, forms, analytics, and performance pass final QA.

Rollback snapshot and owner are recorded.

Publication is approved for the exact revision, then the live page is reverified independently.

CURRENT STATUS  Proposal, workbook, content drafts, and operating plan are complete. Janice review, leadership decisions, WordPress staging, publication approval, and live verification remain open.

BIGORANGE AUTHORITY SYSTEM

# Evidence and source notes

Current verification, dated exports, professional opinion, and approval-gated interview evidence are kept separate.

| Source | Freshness | Use | Boundary |
| --- | --- | --- | --- |
| Janice call recordings | Aug. 28, 2026 | Audience, objections, trust, website, timing, example | Most public permission unresolved |
| Approved paid-pilot proposal | Reconciled Aug. 3, 2026 | Scope, 35 hours, $30/hour, $1,050 | Commercial mechanics open |
| Semrush keyword map | Aug. 4, 2026 | Demand, intent, difficulty, CPC | Dated; not a forecast |
| Moz rankings export | Through Aug. 14, 2026 | Protect existing URL ownership | Not a current live rank check |
| Current builder page | Verified Aug. 28, 2026 | HTTP 200, self-canonical, live copy, JSON-LD | Current state; not replacement approval |
| Google Search documentation | Verified Aug. 28, 2026 | AI features, people-first content, canonical, structured data, FAQ | Official guidance; no outcome promise |
| Web Vitals guidance | Verified Aug. 28, 2026 | Field-performance measurement | Use real-user data for pass/fail |

## Official implementation references

Google Search: Optimizing your website for generative AI features on Google Search

Google Search: Creating helpful, reliable, people-first content

Google Search: Guidance about AI-generated content

Google Search: Canonicalization and duplicate URL guidance

Google Search: Structured data policies and FAQ rich-result changes

Google Search: SEO Starter Guide

Web.dev: Web Vitals

OpenAI and Perplexity crawler-control guidance

FINAL POSITION  Approve the governed foundation first. Publish one coherent hub and two distinct supporting articles. Learn from actual queries and qualified actions. Expand only when the evidence, ownership, and production scope justify the next asset.